## Kunden
Module Name: |  | Kunden
Release Version: |  | 1
Environment tested on(OS/Browser/ExcelVersion/German/English) : |  | German system
Pre-requisites:
Navigation steps: |  | Click on Kunden button in the CalcPro ribbon.
Module Dependencies: |  | Project Meta data
Sno. | Test Scenario | Test Case Description | Test Steps | Test Data | Expected Result | Test Case Type(Positive/Negative) | Test case designed by | Test case design date | Build version 1 | [6 empty] | Build version 2
[9 empty] | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments
1 | Reset the data entered button | To validate the reset button. | 1. Enter some data in the all the fields. 2. Click on the reset button. |  | The data entered by the user must get set to initial state. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
2 | Add new customer button | To validate the add new customer button. | 1. Click on the 'add new customer' button. |  | All the fields of the customer section must set to blank except the customer search field. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
3 | Save button - Customer section | To validate the insertion of the data for the first time. | 1. Enter only the mandatory fields. 2. Click on the Save button. | One field - all mandatory fields | The data entered by the user must get saved. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
4 | Save button - Customer section | To validate the updating of the data. | 1. Select an entry which is already saved. 2. Change the mandatory fields and click in the Save button. | One field | The data changed by the user must get saved and reflected when the customer is loaded again. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
5 | Save button - Customer section | To validate the insertion of the data for the first time. | 1. Enter all the fields for the customer section. 2. Click on the Save button. | All the fields | The data entered by the user must get saved. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
6 | Save button - Customer section | To validate the insertion of the data for the first time. | 1. Select an entry which is already saved. 2. Change the fields and click in the Save button. | All the fields | The data changed by the user must get saved and reflected when the customer is loaded again. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
7 | Save button - Customer section | To validate the updating of the data. | 1. Select an entry having the blank fields. 2. Change the blank value to a field having the a value. | Field with blank to some value | The data entered by the user must get saved. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
8 | Add contact person button | To validate the add contact button. | 1. Select a required customer and click on the 'add contact' button. |  | The adding of the contact person pop up must be displayed. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
9 | Add contact person section | To validate the entry only when the mandatory fields are entered. | 1. Select the required customer and click on the 'add contact' button. 2. Enter the mandatory field and click on the Save button. | Mandatory fields | The entry must get saved. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
10 | Add contact person section | To validate the insertion of the data for the first time. | 1. Select the required customer , click of the 'add contact' button. 2. Enter the mandatory fields and click on the Save button. | One field | The data entered by the user must get saved. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
11 | Add contact person section | To validate the updating of the data. | 1. Select the required customer, select the required entry in the contact perso n section. 2. Make the required changes and click on the Save button. | One field | The data changed by the user must get saved and reflected when the entry is selected again. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
12 | Add contact person section | To validate the insertion of the data for the first time. | 1. Select the required customer , click of the 'add contact' button. 2. Enter all the fields and click on the Save button. | All fields | The data entered by the user must get saved. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
13 | Add contact person section | To validate the updating of the data. | 1. Select the required customer, select the required entry in the contact person section. 2. Make the required changes and click on the Save button. | All fields | The data changed by the user must get saved and reflected when the entry is selected again. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
14 | Add contact person section | To validate the updating of the data. | 1. Select the required customer, select the required entry in the contact person section having the blank fields. 2. Make the required changes and click on the Save button. | Field with blank value to other value | The data changed by the user must get saved and reflected when the entry is selected again. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
15 | Add contact person section | To validate the checked checkbox entry in the contact person section | 1. Select a customer. 2. Select the contact person entry for which the check box is not checked. 3. Change the checkbox and click on the Save button. | Save the check box for multiple rows/entries. | Only one row/entry should have the check box checked. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
16 | Cancel button - Add contact person section | To validate the cancel button in the 'add contact person section'. | 1.Select the customer. 2.Click on 'add contact person' section. 3. Click on Cancel button. |  | 1. The data entered by the user must get reset. 2. The focus should remain in the 'add contact information'. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass |  |  |  | The focus is not retained in the 'add contact section'.
17 | Add address button | To validate the add address button. | 1. Select the customer. 2. Click on the 'add address' button. |  | The 'add address' pop up should be loaded. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
18 | Save button - Add address section | To validate the saving of the record when only mandatory fields are entered. | 1. Select the required customer and click on the 'add address' button. 2. Enter the mandatory field and click on the Save button. | Mandatory fields | The entry should get saved. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
19 | Save button - Add address section | To validate the insertion of the data for the first time. | 1. Select the required customer , click of the 'add address' button. 2. Enter the mandatory fields and click on the Save button. | One field | The data entered by the user must get saved. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
20 | Save button - Add address section | To validate the updating of the data. | 1. Select the required customer, select the required entry in the 'address' section. 2. Make the required changes and click on the Save button. | One field | The data changed by the user must get saved and reflected when the entry is selected again. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
21 | Save button - Add address section | To validate the insertion of the data for the first time. | 1. Select the required customer , click of the 'add contact' button. 2. Enter all the fields and click on the Save button. | All fields | The data entered by the user must get saved. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
22 | Save button - Add address section | To validate the updating of the data. | 1. Select the required customer, select the required entry in the 'address' section. 2. Make the required changes and click on the Save button. | All fields | The data changed by the user must get saved and reflected when the entry is selected again. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
23 | Save button - Add address section | To validate the updating of the data. | 1. Select the required customer, select the required entry in the 'add address' section having the blank fields. 2. Make the required changes and click on the Save button. | Field with blank value to other value | The data changed by the user must get saved and reflected when the entry is selected again. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
24 | Save button - Add address section | To validate the checked checkbox entry in the contact person section | 1. Select a customer. 2. Select the address entry for which the check box is not checked. 3. Change the checkbox and click on the Save button. | Save the check box for multiple rows/entries. | Only one row/entry should have the check box checked. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
25 | Cancel button - Add address section | To validate the 'Cancel' button for the 'add address' section. | 1.Select the customer. 2.Click on the 'add address' button. 3. Click on the Cancel button. |  | 1. The 'adding the address information' pop up should get closed. 2. Main form(Kunden) should be retained. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass |  |  |  | The focus is not retained in the add address section.
26 | Esc key - Kunden form | To validate the 'Esc' key for the 'Kunden' form. | 1. Open the Kuden form. 2. Click on the 'Cancel' button. |  | The 'Kunden' form should get closed. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
27 | Esc key - Contact person form | To validate the 'Esc' key for the 'adding the contact person' pop up. | 1. Open the Kunden form. 2. Click on the 'add contact person' button. 3. Click on the 'Esc' key. |  | The 'adding contact person' pop up should get closed. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Fail | 3719 | UI issue
28 | Esc key - Address form | To validate the 'Esc' key for the 'adding the address' pop up. | 1. Open the Kunden form. 2. Click on the 'add address' button. 3. Click on the 'Esc' key. |  | The 'adding the address' pop up shuld get closed. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
29 | User interface | To validate the user interface of the Kunden form. | 1. Open the Kuden form. 2. Click on the 'Cancel' button. |  | The Labels of each field can be bold and dark. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Fail | 3718 | Enhancement/Suggestions
30 | Kunden form when no projects loaded | To validate the Kunden form, ribbon behavior when there are no projects loaded. | 1.Open the Kunden form when no projects are loaded. |  | The 'Kunden' form should be opened and closed without causing any problem. | Positive | Preethi | 27/07/2020 | Preethi | 28/07/2020 | Pass
31 | Kunden form when a project is loaded | To validate the Kunden form, ribbon behavior when one project is loaded. | 1.Open the Kunden form. 2. Load a project, open different forms of the project. 3. Close the form and reopen the Kunden form. |  | The 'Kunden' form should be opened and closed without causing any problem. | Positive | Preethi | 27/07/2020 | Preethi | 28/07/2020 | Pass
32 | Kunden form when many projects are loaded | To validate the Kunden form when multiple projects are loaded. | 1.Open the Kunden form. 2. Load multiple projects, open different forms of the project. 3. Close the form and reopen the Kunden form. |  | The 'Kunden' form should be opened and closed without causing any problem. | Positive | Preethi | 27/07/2020 | Preethi | 28/07/2020 | Pass
33 | Kunden form from different tabs | To validate the Kunden form in different Generic tabs available. | 1.Open the Kunden form. 2. Tabs different from, open different forms of the from di. 3. Close the form and reopen the Kunden form. |  | The 'Kunden' form should be opened and closed without causing any problem. | Positive | Preethi | 27/07/2020 | Preethi | 28/07/2020 | Pass
34 | Kunden form from different project module tabs | To validate the Kunden form in different tabs of a loaded project. | 1. Open the Kunden form. 2. Click on the Generic tabs in the ribbon. 3. Close the form and reopen the Kunden form. | Dokumente tab | The 'Kunden' form should be opened and closed without causing any problem. | Positive | Preethi | 27/07/2020 | Preethi | 28/07/2020 | Pass
35 | Field comparison for customer section | To validate all the fields for the customer section against the OTTO tool. | Compare all the fields of the Calc pro and the OTTO tool for the customer section. |  | All the fields present in the OTTO tool must be there in the Calc pro tool. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
36 | Field comaprison for 'adding contact person section' | To validate all the fields for the 'adding contact person' section against the OTTO tool. | Compare all the fields of the Calc pro and the OTTO tool for the customer section. | Adding contact perrson pop up | All the fields present in the OTTO tool must be there in the Calc pro tool. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
37 | Field comparison for 'adding the address' section | To validate all the fields for the 'adding address' section against the OTTO tool. | Compare all the fields of the Calc pro and the OTTO tool for the adding address section. | Adding address section pop up | All the fields present in the OTTO tool must be there in the Calc pro tool. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
38 | Search field | To validate the search field of the customers for the newly added customer | 1. Enter the name of the customer to be searched. |  | All the fields of the selected customer must be displayed appropriately. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
39 | Search field | To validate the search field of the customers for the customer for which the fields are updated | 1. Enter the name of the customer to be searched. |  | All the fields of the customer for which the fields has been updated, the updated values must be displayed. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
40 | Search field | To validate the search field of the customer for the old customers. | 1. Enter the name of the customer to be searched. |  | All the fields of the selected customer must be displayed appropriately. | Positive | Preethi | 27/07/2020 | Preethi | 27/07/2020 | Pass
41 | Dependency of the Customer information | To validate the dependency of the customer data in the Project meta data form | 1. Click on the Project meta data form. 2. Click on the customer drop down. |  |  | Positive
42 | Dependency of the Customer information | To validate the dependency of the customer data in the Angebot form | 1. Select a project. 2. Click on the 'Dokumente' tab in the ribbon. 3. Click on the Angebot form and generate the report. |  |  | Positive

## OTTO
Module Name: |  | OTTO
Release Version: |  | 1
Environment tested on(OS/Browser/ExcelVersion/German/English) : |  | German system
Pre-requisites:
Navigation steps:
Module Dependencies: |  | In Angebot report
Sno. | Test Scenario | Test Case Description | Test Steps | Test Data | Expected Result | Test Case Type(Positive/Negative) | Test case designed by | Test case design date | Build version 1 | [6 empty] | Build version 2
[9 empty] | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments
1 | Reset the data entered button | To validate the reset button. | 1. Enter some data in the all the fields. 2. Click on the reset button. |  | The data entered by the user must get set to initial state. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
2 | Add new company button | To validate the add new company button. | 1. Click on the 'add new company' button. |  | All the fields of the company section must set to blank except the company search field. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
3 | Save button - company section | To validate the insertion of the data for the first time. | 1. Enter only the mandatory fields. 2. Click on the Save button. | One field - all mandatory fields | The data entered by the user must get saved. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
4 | Save button - company section | To validate the updating of the data. | 1. Select an entry which is already saved. 2. Change the mandatory fields and click in the Save button. | One field | The data changed by the user must get saved and reflected when the company is loaded again. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
5 | Save button - company section | To validate the insertion of the data for the first time. | 1. Enter all the fields for the company section. 2. Click on the Save button. | All the fields | The data entered by the user must get saved. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
6 | Save button - company section | To validate the insertion of the data for the first time. | 1. Select an entry which is already saved. 2. Change the fields and click in the Save button. | All the fields | The data changed by the user must get saved and reflected when the company is loaded again. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
7 | Save button - company section | To validate the updating of the data. | 1. Select an entry having the blank fields. 2. Change the blank value to a field having the a value. | Field with blank to some value | The data entered by the user must get saved. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
8 | Company section - checkbox | To validate the checkbox for the second after one entry has been saved with the checkbox | 1. Select a required company entry and click on the 'add contact' button. |  | The check box must not be checked unless the user explicitly selects the checkbox. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Fail | 3720 | UI issue |  | The check box once checked for one of the entry, it is being checked for all the other entries which is created after the checked entry.
9 | Add contact person button | To validate the add contact button. | 1. Select the required company entry entry and click on the 'add contact' button. 2. Enter the mandatory field and click on the Save button. |  | The adding of the contact person pop up must be displayed. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
| Add contact person | To validate the creation of the entry only when the mandatory fields are entered. | 1. Select the required company entry , click of the 'add contact' button. 2. Enter the mandatory fields and click on the Save button. | Mandatory fields |  | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Fail
10 | Add contact person section | To validate the insertion of the data for the first time. | 1. Select the required company entry, select the required entry in the contact perso n section. 2. Make the required changes and click on the Save button. | One field | The data entered by the user must get saved. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
11 | Add contact person section | To validate the updating of the data. | 1. Select the required company entry , click of the 'add contact' button. 2. Enter all the fields and click on the Save button. | One field | The data changed by the user must get saved and reflected when the entry is selected again. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
12 | Add contact person section | To validate the insertion of the data for the first time. | 1. Select the required company entry, select the required entry in the contact person section. 2. Make the required changes and click on the Save button. | All fields | The data entered by the user must get saved. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
13 | Add contact person section | To validate the updating of the data. | 1. Select the required company entry, select the required entry in the contact person section having the blank fields. 2. Make the required changes and click on the Save button. | All fields | The data changed by the user must get saved and reflected when the entry is selected again. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
14 | Add contact person section | To validate the updating of the data. | 1. Select a company. 2. Select the contact person entry for which the check box is not checked. 3. Change the checkbox and click on the Save button. | Field with blank value to other value | The data changed by the user must get saved and reflected when the entry is selected again. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
15 | Add contact person section | To validate the checked checkbox entry in the contact person section | 1.Select the company. 2.Click on 'add contact person' section. 3. Click on Cancel button. | Save the check box for multiple rows/entries. | Only one row/entry should have the check box checked. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
16 | Cancel button - Add contact person section | To validate the cancel button in the 'add contact person section'. | 1. Select a company. 2. Click on the 'add contact person' button. 3. Click on the Cancel button. |  | 1. The data entered by the user must get reset. 2. The focus should be retained in the add contact person information. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass |  |  |  | The focus in not retained in the 'add contact person'.
17 | Esc key - OTTO form | To validate the 'Esc' key for the 'OTTO ' form. | 1. Open the OTTO form. 2. Click on the 'Esc' key. |  | The 'OTTO ' form should get closed. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Fail | 3719 | UI issue
18 | Esc key - Contact person form | To validate the 'Esc' key for the 'adding the contact person' pop up. | 1. Open the OTTO form. 2. Select a company. 3. Click on the 'add contact person' button. 4. Click on the 'Esc' key. |  | The 'adding contact person' pop up should get closed. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
19 | User interface | To validate the user interface of the OTTO form. | 1. Click on the OTTO form. |  | The Labels of each field can be bold and dark. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Fail | 3718 | UI issue
20 | OTTO form when no projects loaded | To validate the OTTO form when there are no projects loaded. | 1. Open the OTTO form. 2. Close the form. |  | The 'OTTO ' form should be opened and closed without causing any problem. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
21 | OTTO form when a project is loaded | To validate the OTTO form when one project is loaded. | 1. Load particular project, open some project tabs. 2. Open the OTTO form. 3. Close the project form. |  | The 'OTTO ' form should be opened and closed without causing any problem. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
22 | OTTO form when many projects are loaded | To validate the OTTO form when multiple projects are loaded. | 1. Load multiple projects, open some of the project tabs. 2. Open the OTTO form. 3. Close the project form. |  | The 'OTTO ' form should be opened and closed without causing any problem. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
23 | OTTO form for different tabs | To validate the OTTO form in different Generic tabs available. | 1. Load a project click on the 'Dokumente tab'. 2. Open the OTTO form. 3. Click on the Close button. |  | The 'OTTO ' form should be opened and closed without causing any problem. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
24 | OTTO form from different project module tabs | To validate the OTTO form in different tabs of a loaded project. | 1. Load multiple projects, open some of the project tabs. 2. Open the OTTO form. 3. Close the project form. |  | The 'OTTO ' form should be opened and closed without causing any problem. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
25 | Field comparison for company section | To validate all the fields for the company section against the OTTO tool. | 1. Compare the fields in the Calc pro and OTTO pro tool for the Company section. |  | All the fields present in the OTTO tool must be there in the Calc pro tool. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
26 | Field comaprison for 'adding contact person section' | To validate all the fields for the 'adding contact person' section against the OTTO tool. | 1. Compare the fields in the Calc pro and OTTO pro tool for the Contact section. |  | All the fields present in the OTTO tool must be there in the Calc pro tool. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
27 | Search field | To validate the search field of the customers for the newly added customer | 1. Enter the required company name. |  | All the fields of the selected customer must be displayed appropriately. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Fail | 3721 | UI issue |  | Click on the 'search drop down' key the OTTO section is shifting down and again reset to normal state.
28 | Search field | To validate the search field of the customers for the customer for which the fields are updated | 1. Enter the required company name. |  | All the fields of the customer for which the fields has been updated, the updated values must be displayed. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
29 | Search field | To validate the search field of the customer for the old customers. | 1. Enter the required company name. |  | All the fields of the selected customer must be displayed appropriately. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass

## Lieferant
Module Name: |  | Lieferant
Release Version: |  | 1
Environment tested on(OS/Browser/ExcelVersion/German/English) : |  | German system
l
Pre-requisites:
Navigation steps:
Module Dependencies: |  | Supply proposal, Update Supply Proposal
Sno. | Test Scenario | Test Case Description | Test Steps | Test Data | Expected Result | Test Case Type(Positive/Negative) | Test case designed by | Test case design date | Build version 1 | [6 empty] | Build version 2
[9 empty] | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments
1 | Reset the data entered button | To validate the reset button. | 1. Enter some data in the all the fields. 2. Click on the reset button. |  | The data entered by the user must get set to initial state. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
2 | Add new Lieferant button | To validate the add new Lieferant button. | 1. Click on the 'add new Lieferant' button. |  | All the fields of the Lieferant section must set to blank except the Lieferant search field. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
3 | Save button - Lieferant section | To validate the insertion of the data for the first time. | 1. Enter only the mandatory fields. 2. Click on the Save button. | One field - all mandatory fields | The data entered by the user must get saved. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Fail |  | UI issue |  | The button text is not visible completely.
4 | Save button - Lieferant section | To validate the updating of the data. | 1. Select an entry which is already saved. 2. Change the mandatory fields and click in the Save button. | One field | The data changed by the user must get saved and reflected when the Lieferant is loaded again. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
5 | Save button - Lieferant section | To validate the insertion of the data for the first time. | 1. Enter all the fields for the Lieferant section. 2. Click on the Save button. | All the fields | The data entered by the user must get saved. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
6 | Save button - Lieferant section | To validate the insertion of the data for the first time. | 1. Select an entry which is already saved. 2. Change the fields and click in the Save button. | All the fields | The data changed by the user must get saved and reflected when the Lieferant is loaded again. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
7 | Save button - Lieferant section | To validate the updating of the data. | 1. Select an entry having the blank fields. 2. Change the blank value to a field having the a value. | Field with blank to some value | The data entered by the user must get saved. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
8 | Add contact person button | To validate the add contact button. | 1. Select a required customer and click on the 'add contact' button. |  | The adding of the contact person pop up must be displayed. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Fail |  | UI issue |  | The button text is not visible completely.
| Add contact person section | To validate the creation of the entry when only the mandatory field has been entered. | 1. Select the required customer and click on the 'add contact' button. 2. Enter the mandatory field and click on the Save button. | Mandatory fields | The entry must get created. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
9 | Add contact person section | To validate the insertion of the data for the first time. | 1. Select the required customer , click of the 'add contact' button. 2. Enter the mandatory fields and click on the Save button. | One field | The data entered by the user must get saved. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
10 | Add contact person section | To validate the updating of the data. | 1. Select the required customer, select the required entry in the contact person section. 2. Make the required changes and click on the Save button. | One field | The data changed by the user must get saved and reflected when the entry is selected again. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
11 | Add contact person section | To validate the insertion of the data for the first time. | 1. Select the required Lieferant , click of the 'add contact' button. 2. Enter all the fields and click on the Save button. | All fields | The data entered by the user must get saved. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
12 | Add contact person section | To validate the updating of the data. | 1. Select the required Lieferant, select the required entry in the contact person section. 2. Make the required changes and click on the Save button. | All fields | The data changed by the user must get saved and reflected when the entry is selected again. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
13 | Add contact person section | To validate the updating of the data. | 1. Select the required Lieferant, select the required entry in the contact person section having the blank fields. 2. Make the required changes and click on the Save button. | Field with blank value to other value | The data changed by the user must get saved and reflected when the entry is selected again. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
14 | Add contact person section | To validate the checked checkbox entry in the contact person section | 1. Select a lieferant. 2. Select the contact person entry for which the check box is not checked. 3. Change the checkbox and click on the Save button. | Save the check box for multiple rows/entries. | Only one row/entry should have the check box checked. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
15 | Add contact person section | To validate the validation of the Save button when the entry is saved without any data. | 1.Select the Lieferant. 2.Click on 'add contact person' section. 3. Click on Cancel button. |  | 1. The form must get closed. 2. The focus should be set back to the Lieferant form. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Fail |  | Functional issue |  | Entry is getting created without any data.
16 | Cancel button - Add contact person section | To validate the cancel button in the 'add contact person section'. | 1. Select the Lieferant. 2. Click on the 'add address' button. |  | 1. The data entered by the user must get reset. 2. The focus should remain in the 'add contact information'. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass |  |  |  | The text is not visible completely on the button.
17 | Add address button | To validate the add address button. | 1. Select the required Lieferant and click on the 'add address' button. 2. Enter the mandatory field and click on the Save button. |  | The 'add address' pop up should be loaded. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass |  |  |  | The blank space can be reduced
| Save button - Add address section | To validate the saving of the record when only mandatory fields are entered. | 1. Select the required Lieferant , click of the 'add address' button. 2. Enter the mandatory fields and click on the Save button. |  | Appropriate error message or validation message must be displayed as "Please fill the mandatory fields". | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Fail |  | Functional issue |  | Entry is getting created without any data.
18 | Save button - Add address section | To validate the insertion of the data for the first time. | 1. Select the required Lieferant, select the required entry in the 'address' section. 2. Make the required changes and click on the Save button. | One field | The data entered by the user must get saved. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
19 | Save button - Add address section | To validate the updating of the data. | 1. Select the required Lieferant , click of the 'add contact' button. 2. Enter all the fields and click on the Save button. | One field | The data changed by the user must get saved and reflected when the entry is selected again. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
20 | Save button - Add address section | To validate the insertion of the data for the first time. | 1. Select the required Lieferant, select the required entry in the 'address' section. 2. Make the required changes and click on the Save button. | All fields | The data entered by the user must get saved. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
21 | Save button - Add address section | To validate the updating of the data. | 1. Select the required Lieferant, select the required entry in the 'add address' section having the blank fields. 2. Make the required changes and click on the Save button. | All fields | The data changed by the user must get saved and reflected when the entry is selected again. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
22 | Save button - Add address section | To validate the updating of the data. | 1. Select the required Lieferant, select the required entry in the contact person section having the blank fields. 2. Make the required changes and click on the Save button. | Field with blank value to other value | The data changed by the user must get saved and reflected when the entry is selected again. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
23 | Save button - Add address section | To validate the checked checkbox entry in the contact person section | 1. Select a Lieferant. 2. Select the address entry for which the check box is not checked. 3. Change the checkbox and click on the Save button. | Save the check box for multiple rows/entries. | Only one row/entry should have the check box checked. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
24 | Save button - Add address section | To validate the cancel button in the 'add contact person section'. | 1.Select the Lieferant. 2.Click on the 'add address' button. 3. Click on the Cancel button. |  | 1. The 'adding the address information' pop up should get closed. 2. Main form(Lieferant) should be retained. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
25 | Cancel button - Add address section | To validate the 'Cancel' button for the 'add address' section. | 1. Select the required Lieferant. 2. Click on the 'add address button'. 3. Click on the Cancel button. |  | 1.The action/ data entered by the user must reset. 2. The focus should remain in the 'add address' section. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
26 | Add articles button | To validate the 'add article button' | 1. Select the required Lieferant. 2. Click on the 'add articles button'. |  | The add articles pop up must be displayed. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
27 | Save button - Add article section | To validate adding of the article to the Lieferant. | 1. Select the required Lieferant. 2. Click on the 'add articles button'. 3. Enter the article number and click on the Save button. |  | The data entered by the user must get saved. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass |  |  |  | 1.Can provide a drop down for the supplier along with the text field to enter the value. 2. Text for the Save button is not completely visible.
28 | Cancel button - Add article section | To validate the cancel button in the 'add article' section. | 1. Select the required Lieferant. 2. Click on the 'add articles button'. 3. Click on the 'Cancel' button. |  | The 'add article pop up' must be closed. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass |  |  |  | Text is not completely visible on the button
29 | Close button - Add article section | To validate the close button in the 'add article' section. | 1. Select the required Lieferant. 2. Click on the 'add articles button'. 3. Click on the 'Close' button. |  | The 'add article pop up' must be closed. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
30 | Esc key - Lieferant form | To validate the 'Esc' key for the 'Lieferant' form. | 1. Open the Lieferant form. 2. Click on the 'Esc' key. |  | The 'Lieferant' form should get closed. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
31 | Esc key - Contact person form | To validate the 'Esc' key for the 'adding the contact person' pop up. | 1. Open the Lieferant form. 2. Select a Lieferant, click on the 'add contact person' section. Click on the 'Esc' key. |  | The 'adding contact person' pop up should get closed. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Fail |  | UI issue |  | Not working
32 | Esc key - Address form | To validate the 'Esc' key for the 'adding the address' pop up. | 1. Open the Lieferant form. 2. Select a Lieferant, click on the 'add address' section. 3. Click on the 'Esc' key. |  | The 'adding the address' pop up shuld get closed. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
33 | Esc key - add article section | To validate the 'Esc' key for the 'adding the article' pop up. | 1. Open the Lieferant form. 2. Select a Lieferant, click on the 'add article' section. 3. Click on the 'Esc' key. |  | The 'add article pop up' must be closed. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
34 | User interface | To validate the user interface of the Lieferant form. | 1. Open the Lieferant form. |  | The Labels of each field can be bold and dark. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
35 | Lieferant form when no projects loaded | To validate the Lieferant form when there are no projects loaded. | 1. Open the Lieferant form. 2. Close the form. |  | The 'Lieferant' form should be opened and closed without causing any problem. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
36 | Lieferant form when a project is loaded | To validate the Lieferant form when one project is loaded. | 1. Load a required project. 2. Click on the required tab. 3. Open the Lieferant form from the Calc pro tab. 4. Close the Lieferant form. |  | The 'Lieferant' form should be opened and closed without causing any problem. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
37 | Lieferant form when many projects are loaded | To validate the Lieferant form when multiple projects are loaded. | 1. Load multiple projects. 2. Click on the required tab. 3. Open the Lieferant form. 4. Close the Lieferant form. |  | The 'Lieferant' form should be opened and closed without causing any problem. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
38 | Lieferant form from different tabs | To validate the Lieferant form in different Generic tabs available. | 1. Load a project. 2. Click on the 'Dokumente' tab. 3. Open the Lieferant form. 4. Close the Lieferant form. |  | The 'Lieferant' form should be opened and closed without causing any problem. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
39 | Field comparison for Lieferant section | To validate all the fields for the Lieferant section against the OTTO tool. | 1. Compare all the fields of the Liefrant section in Calc pro and OTTO pro tool. |  | All the fields present in the OTTO tool must be there in the Calc pro tool. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
40 | Field comaprison for 'adding contact person section' | To validate all the fields for the 'adding contact person' section against the OTTO tool. | 1. Compare all the fields of the 'add contact person' section in Calc pro and OTTO pro tool. |  | All the fields present in the OTTO tool must be there in the Calc pro tool. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
41 | Field comparison for 'adding the address' section | To validate all the fields for the 'adding address' section against the OTTO tool. | 1. Compare all the fields of the 'add address' section in Calc pro and OTTO pro tool. |  | All the fields present in the OTTO tool must be there in the Calc pro tool. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
42 | Search field | To validate the search field of the Lieferants for the newly added Lieferant | 1. Enter the required Lieferant name and click on the Search button. |  | All the fields of the selected Lieferant must be displayed appropriately. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
43 | Search field | To validate the search field of the Lieferants for which the fields are updated | 1. Enter the required Lieferant name and click on the Search button. |  | All the fields of the Lieferant for which the fields has been updated, the updated values must be displayed. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
44 | Search field | To validate the search field of the Lieferant for the old Lieferants. | 1. Enter the required Lieferant name and click on the Search button. |  | All the fields of the selected Lieferant must be displayed appropriately. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Pass
45 | Status bar | To validate the content displayed in the Status bar. | 1. Click on the Save button for saving the Lieferant information |  | The success message of saving the Lieferant must be displayed in the Status bar. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020 | Fail |  | UI issue |  | The text displayed in the status bar is not significantly visible.
46 | Dependency of the Lieferant information | To validate the dependency of the Lieferant data in the Supply proposal form of Project. | 1. Load a project. 2. Click on the Supply proposal. 3. Click on the articles present in the project. |  | All the suppliers mapped to the particular article must be listed in the supplier list. | Positive | Preethi | 28/07/2020 | Preethi | 28/07/2020

## Article
Module Name: |  | Article stammdata
Release Version: |  | 1
Environment tested on(OS/Browser/ExcelVersion/German/English) : |  | German system
Pre-requisites:
Navigation steps:
Module Dependencies: |  | Supply proposal, Update Supply Proposal
Sno. | Test Scenario | Test Case Description | Test Steps | Test Data | Expected Result | Test Case Type(Positive/Negative) | Test case designed by | Test case design date | Build version 1 | [6 empty] | Build version 2
[9 empty] | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments
1 | Adding a new article | To validate adding the new article. |  | Mandatory fields only(WG and WA) | The new supplier entry must get created. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass | 3726 | Enhancement/Suggestions
2 | Adding a new article | To validate adding new article |  | All the fields(WG, WA and WI) | The new supplier entry must get created. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
3 | Adding a new article | To validate adding new article |  | Without entering the mandatory fields | Appropriate warning message must be displayed. | Negative | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
4 | Adding a new article - Continous check box | To validate the new continuous check box |  | Mandatory fields only(WG and WA) | The supplier should get saved and the new mode must be retained | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
5 | Adding a new article - Continous check box | To validate the new continuous check box |  | All the fields(WG, WA and WI) | The supplier should get saved and the new mode must be retained | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
6 | Adding a new article - Continous check box | To validate the new continuous check box |  | Without entering the mandatory fields | Appropriate warning message must be displayed. | Negative | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
7 | Adding new dimension | To validate adding the new dimensions |  | Mandatory fields | The new dimension must get added for the selected article. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
8 | Adding new dimension | To validate adding the new dimensions |  | All the fields | The new dimension must get added for the selected article. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
9 | Adding new dimension | To validate adding the new dimensions |  | Without entering the mandatory fields | Appropriate warning message must be displayed. | Negative | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
10 | Updating the article | To validate updatin g of the article |  | One field | The supplier must get updated correctly. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
11 | Updating the article | To validate the updating of the complete article information |  | All the fields | The supplier must get updated correctly. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
12 | Deleting the article | To validate deletion of the article |  | Complete article with dimensions | The article and the related dimensions must get deleted | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
13 | Deleting the article | To validate deleting WI of the article. |  | Only WI | The selected WI entry must be deleted | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
14 | Deleting the Dimension | To validate the deletion of the dimension |  |  | The selected dimension must get deleted from the selected validity period. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
15 | Gultigkeitsdatum button | To validate editing of the dimension for material list price |  | Material list price | 1.The changes made to the list price of the dimension must be saved. 2. The value of the dimension in other validity periods should not be affected/changed. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
16 | Gultigkeitsdatum button | To validate editing of the dimension for minutes field |  | Minutes | 1.The changes made to the minutes of the dimension must be saved. 2. The value of the dimension in other validity periods should not be affected/changed. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
17 | Gultigkeitsdatum button | To validate editing of the dimension for Material list price and Minutes |  | Both Material list price and minutes | 1.The changes made to the list price and minutes of the dimension must be saved. 2. The value of the dimension in other validity periods should not be affected/changed. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
18 | Gultigkeitsdatum button | To validate the editing of the dimension for one entry for a validity period |  | One entry | 1.The changes made to the list price and minutes of the dimension must be saved. 2. The value of the dimension in other validity periods should not be affected/changed. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
19 | Gultigkeitsdatum button | To validate the editing of the dimension for multiple entries for a validity period |  | Multiple entry | 1.The changes made to the list price and minutes of all the dimension must be saved. 2. The value of the dimension in other validity periods should not be affected/changed. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
20 | Gultigkeitsdatum button | To validate the editing of the dimensions for multiple entries of a period. |  | For multiple validity periods | The changes made to the dimensions a particular validity period must not affect the values of the dimension of the other validity period. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
21 | Listprice abandern button | To validate the creation of the new validity period for period different periods. |  | January - period greater than the current period | 1.New set of validity period must get created based on the current validity period loaded in the article. 2.All the dimensions of the loaded validity period must be copied for the new validity period. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
22 | Listprice abandern button | To validate the creation of the new validity period for period different periods. |  | June - period greater than the current period | 1.New set of validity period must get created based on the current validity period loaded in the article. 2.All the dimensions of the loaded validity period must be copied for the new validity period. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
23 | Listprice abandern button | To validate the creation of the new validity period for period different periods. |  | December - period greater than the current period. | 1.New set of validity period must get created based on the current validity period loaded in the article. 2.All the dimensions of the loaded validity period must be copied for the new validity period. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
24 | Rabatt mapping | To validate the rabatt mapping for the Article |  |  | 1.The rabatt mapping must be fetched from the Rabatt form. 2. The multi values loaded to the dimensions must be based on the multi values present for the Rabatt. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass | 3739 | UI issue
25 | UI design | To validate the UI design for the article form. |  |  | All the button, labels texts and all the form design must be correct. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Fail | 3724 | UI issue
26 | Fields comparison | To validate all the fields present in the article form |  |  | All the fields present for the OTTO pro must be present in the Calc pro article form. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
27 | Fields comparison | To validate all the fields in the 'add dimensions'. |  |  | All the fields present for the OTTO pro must be present in the Calc pro article - add dimension sub-form. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
28 | Loading the Article form | To validate loading the article form when no projects are loaded |  |  | The article form must get loaded without any problem | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
29 | Loading the Article form | To validate the loading of the article form when a project has been loaded. |  |  | The article form must get loaded without any problem | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
30 | Loading the Article form | To validate the loading of the article form when multiple projects has been loaded. |  |  | The article form must get loaded without any problem | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020 | Pass
31 | Dependency | To validate the dependency of the article in L V details form |  |  | The articles and its value must be loaded to the positions, when the article has been entered in the positions. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020
32 | Dependency | To validate the dependency of the article in supply proposal form |  |  | The supplier mapped with the articles must be listed in the Supply proposal form when the article has been selected. | Positive | Preethi | 2020-04-08 | Preethi | 29/07/2020

## Typ
Module Name: |  | Typ
Release Version: |  | 1
Environment tested on(OS/Browser/ExcelVersion/German/English) : |  | German system
Pre-requisites:
Navigation steps:
Module Dependencies: |  | Rabatt and Articles master
Sno. | Test Scenario | Test Case Description | Test Steps | Test Data | Expected Result | Test Case Type(Positive/Negative) | Test case designed by | Test case design date | Build version 1 | [6 empty] | Build version 2
[9 empty] | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments
1 | Creating the Typ | To validate the creation of the Typ mapping by entering the all the fields |  | All the fields | The Typ record must be created. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020 | Pass | 3731 | Enhancement/Suggestions
2 | Creating the Typ | To validate the creation of the Typ mapping when mandatory fields are not entered |  | Mandatory fields blank | Appropriate validation message must be displayed. | Negative | Preethi | 2020-05-08 | Preethi | 29/07/2020 | Fail | 3730 | UI issue
3 | Deleting of the Typ | To validate the deletion of the Typ entry when it is not used in any Rabatt group. |  |  | The Typ entry must get deleted without any error. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020 | Pass
4 | Deleting of the Typ | To validate the deletion of the Typ entry when it is used in the Rabatt group. |  |  | Appropriaterror message must be displayed as "The Typ has been used in the projects". | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020 | Pass
5 | Esc key | To validate the 'Esc' key functionality in the Typ form |  |  | The form should be closed and the focus must be on the previous active tab. | [5 empty] | Pass
6 | Fields comparison | To validate all the fields present in the Typ form |  |  | All the fields in the OTTO pro tool must be present in the Calc pro Typ form. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020 | Pass
7 | UI design | To validate the UI design of the Typ form. |  |  | All the button, labels texts and all the form design must be correct. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020 | Fail | 3728 | UI issue
8 | Loading of the Typ form | To validate loading of the Typ form when no projects are loaded |  |  | The Typ form should be loaded without any problem. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020 | Pass
9 | Loading of the Typ form | To validate the Typ form when a project has been loaded |  |  | The Typ form should be loaded without any problem. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020 | Pass
10 | Loading of the Typ form | To validate the Typ form when multiple projects are loaded. |  |  | The Typ form should be loaded without any problem. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020 | Pass
11 | Loading of the Typ form | To validate the Typ form when Dokumente tab is loaded for a particular project. |  |  | The Typ form should be loaded without any problem. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020 | Pass

## Rabatt
Module Name: |  | Rabatt
Release Version: |  | 1
Environment tested on(OS/Browser/ExcelVersion/German/English) : |  | German system
Pre-requisites:
Navigation steps:
Module Dependencies: |  | Article master
Sno. | Test Scenario | Test Case Description | Test Steps | Test Data | Expected Result | Test Case Type(Positive/Negative) | Test case designed by | Test case design date | Build version 1 | [6 empty] | Build version 2
[9 empty] | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments
1 | Adding new Rabatt group | To validate the creation of the Rabatt by entering the all the fields |  | All the fields | The Rabatt record must be created. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020 |  | 3735 | Enhancement/Suggestions
2 | Adding new Rabatt group | To validate the creation of the Rabatt without entering the mandatory fields |  | Without the mandatory fields | Appropriate validation message must be displayed. | Negative | Preethi | 2020-05-08 | Preethi | 29/07/2020
3 | Editing the multi values of the Rabatt | To validate the editing of the multi value. |  | For multi 1 field = 0.11 | The changed multi value must be updated in the grid for the selected Rabatt | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
4 | Editing the multi values of the Rabatt | To validate the editing of all the multi values. |  | for all multi's enter 1 - 0.11 2 - 1.12 3 - 0.45 4 - 1.14 | The changed multi value must be updated in the grid for the selected Rabatt | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
5 | Adding the Typ to the Rabatt. | To validate adding of the Typ to the Rabatt group. |  |  | The selected Typ must be mapped to the Rabatt. | Positive | Preethi | 43959 | Preethi | 29/07/2020 |  | 3734 | Enhancement/Suggestions
[12 empty] | 3733 | Enhancement/Suggestions
6 | Cancel button - Adding Typ form | To validate the cancel button in the 'adding Typ' form. |  | Cancel button | The 'add Typ' form must get closed. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
7 | Close button - Adding Typ form | To validate the close button in the 'adding Typ' form. |  | Close button | The 'add Typ' form must get closed. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
8 | Esc key - Adding Typ form | To validate the 'Esc' key in the 'add Typ' form |  | 'Esc' key | The 'add Typ' form must get closed. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
9 | Reset data button | To validate the reset button for the Rabatt section. |  | Reset button | The data entered by the user must get reset. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
10 | Creating the new Rabatt from existing Rabatt | To validate the creation of the Rabatt from the existing Rabatt for the period less than the current period |  | Existing period - January 2020 New period - December 2019 | The new Rabatt for a new period must be created using the existing period. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020 |  | 3736 | Enhancement/Suggestions
11 | Creating the new Rabatt from existing Rabatt | To validate the creation of the Rabatt from the existing Rabatt for the period greater than the current period |  | Existing period - January 2020 New period - February 2019 | The new Rabatt for a new period must be created using the existing period. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
12 | Creating the new Rabatt from existing Rabatt | To validate the creation of the Rabatt from the existing Rabatt for the period equal than the current period |  | Existing period - January 2020 New period - January 2020 | The new Rabatt for a new period must be created using the existing period. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
13 | Deleting the Typ from the Rabatt | To validate the deletion of the Typ mapping from Rabatt. |  |  | The Typ must be removed from the Rabatt group. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
14 | Esc key - Rabatt form | To validate the 'Esc' key in the Rabatt form. |  | 'Esc' key | The Rabatt form must get closed. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
15 | Close Button - Rabatt form | To validate the Close button in the Rabatt form. |  | Close button | The Rabatt form must get closed. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
16 | UI design | To validate the UI design of the Rabatt form. |  |  | All the button, labels texts and all the form design must be correct. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020 |  | 3732 | UI issue
17 | Field comparison | To validate all the fields present in the Rabatt form |  |  | All the fields in the OTTO pro tool must be present in the Calc pro Rabatt form. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
18 | Field comparison | To validate all the fields present in the Rabatt form |  |  | All the fields in the OTTO pro tool must be present in the Calc pro 'add Typ' subform. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
19 | Loading the Rabatt form | To validate loading of the Rabatt form when no projects are loaded |  |  | The Rabatt form should be loaded without any problem. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
20 | Loading the Rabatt form | To validate the Rabatt form when a project has been loaded |  |  | The Rabatt form should be loaded without any problem. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
21 | Loading the Rabatt form | To validate the Rabatt form when multiple projects are loaded. |  |  | The Rabatt form should be loaded without any problem. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020
22 | Loading the Rabatt form | To validate the Rabatt form when Dokumente tab is loaded for a particular project. |  |  | The Rabatt form should be loaded without any problem. | Positive | Preethi | 2020-05-08 | Preethi | 29/07/2020

## Add accessories
Module Name: |  | Add accessories
Release Version: |  | 1
Environment tested on(OS/Browser/ExcelVersion/German/English) : |  | German system
Pre-requisites:
Navigation steps:
Module Dependencies: |  | LV details
Sno. | Test Scenario | Test Case Description | Test Steps | Test Data | Expected Result | Test Case Type(Positive/Negative) | Test case designed by | Test case design date | Build version 1 | [6 empty] | Build version 2
[9 empty] | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments
1 | Creating the accessories | To validate the adding of the articles to the accessories |  | For - 8/5/1 Add article - 8/6/1 | 1. The accessory mapping must be created and the article of the accessories must be listed in the grid below. 2. The 'Has accessories' column should change to 'Yes'. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
2 | Creating the accessories | To validate the adding of multiple article to the accessory |  | For - 8/6/1 Add article - 8/7/1, 8/8/1 | 1. The accessory mapping must be created and all the articles of the accessories must be listed in the grid below. 2. The 'Has accessories' column should change to 'Yes'. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
3 | Creating the accessories | To validate the creation of the accessories without entering the mandatory fields. |  | For - 8/5/1 Save the value without entering the values. | Appropriate validation symbol/message must be displayed. | Negative | Preethi | 2020-06-08 | Preethi | 30/07/2020
4 | Removing the article from accessory | To validate removing of an article from accessory |  | For - 8/5/1 Remove article - 8/6/1 | 1. The article must be removed from the accessory list. 2. If accessory had only one article, then the 'Has accessories' column must set to 'No' other wise 'Yes'. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
5 | Removing the article from accessory | To validate removal of all the articles from the accessory |  | For - 8/6/1 Remove article - 8/7/1, 8/8/1 | 1. The articles must be removed from the accessory list. 2. If accessory had only one article, then the 'Has accessories' column must set to 'No'. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
6 | Cancel button - 'add accessories' sub form | To validate the Cancel button in the 'add accessories' sub form. |  |  | The 'add accessory' form must get closed and focus must be returned to the main form. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
7 | Close button - 'add accessories' sub form | To validate the Close button in the 'add accessories' sub form. |  |  | The 'add accessory' form must get closed and focus must be returned to the main form. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
8 | Esc' key 'add accessories' sub form | To validate the 'Esc' key in the add accessories sub form. |  |  | The 'add accessory' form must get closed and focus must be returned to the main form. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
9 | Close button - 'add accessories' main form | To validate the Close button in the 'add accessories' main form. |  |  | The 'add accessory' form must get closed and focus must be returned to the Calc pro ribbon. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
10 | Esc' key add accessories main form | To validate the 'Esc' key in the add accessories main form. |  |  | The 'add accessory' form must get closed and focus must be returned to the Calcpro ribbon. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
11 | UI design | To validate the UI design of 'add accessories' form. |  |  | All the button, labels texts and all the form design must be correct. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
12 | Field comparison | To validate all the fields of the 'add accessories' main form. |  |  | All the fields in the OTTO pro tool must be present in the Calc pro add accessories main form. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
13 | Field comparison | To validate all the fields of the 'add accessories' sub form. |  |  | All the fields in the OTTO pro tool must be present in the Calc pro add accessories subform. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
14 | Loading the form | To validate the loading of the 'add accessories' form when no projects are loaded |  |  | The 'add accessories' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020 |  | 3740 | UI issue | Open
15 | Loading the form | To validate the loading of the 'add accessories' form when one project is loaded |  |  | The 'add accessories' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
16 | Loading the form | To validate the loading of the 'add accessories' form when multiple projects are loaded |  |  | The 'add accessories' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
17 | Loading the form | To validate loading of the 'add accessories' form when the focus is on the Dokumente tab of the project. |  |  | The 'add accessories' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
18 | Dependency | To validate the dependecy of the 'add accessories' form in the LV details positions. |  |  | The accessory added in the form, on clicking on the add accessory button in the LV details position, the mapping of the accessory must be displayed. | Positive | Preethi | 2020-06-08

## Datanorm
Module Name: |  | Datanorm
Release Version: |  | 1
Environment tested on(OS/Browser/ExcelVersion/German/English) : |  | German system
Pre-requisites:
Navigation steps:
Module Dependencies: |  | Article master, Lieferant
Sno. | Test Scenario | Test Case Description | Test Steps | Test Data | Expected Result | Test Case Type(Positive/Negative) | Test case designed by | Test case design date | Build version 1 | [6 empty] | Build version 2
[9 empty] | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments
1 | Import | To validate the Importing of the selected file. |  | .001 file | The data must get imported into the form successfully. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
2 | Import | To validate the importing of the invalid file. |  | file which is not having .001 extension | Appropriate error message must be displayed as "Not a datanorm file". | Negative | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
3 | Import - Cancel button | To validate the Cancel button in the import dialog. |  |  | The file import must get Cancelled. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
4 | New button | To validate the New button. |  |  | 1.The new file will be opened. 2.The existing data will be minimized. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
5 | Save button | To validate the saving of the Imported file. |  |  | The imported data must get saved with in Excel format. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
6 | Save as button | To validate the Save as option for the imported data. |  |  | The imported data must get saved in the new file. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
7 | Open the Excel file | To validate loading the Excel data. |  |  | The data in the Excel file must be loaded in the Datanorm form. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
8 | Open the Excel file | To validate the Cancel button in the open file dialog. |  |  | The opening of the Excel file dialog must get closed. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
9 | Import - on Existing data | To validate the Importing of the file when there is some data in the Datanorm file. |  |  | 1. Message must be displayed to the user as "Do you want to replace the existing data?" 2. If user selects as "Yes" - then the data must get replaced. 3. If user selects as "No" - then the data must not get replaced. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
10 | Open file on Existing data | To validate the loading of the file when there is some data in the Datanorm file. |  |  | 1. Message must be displayed to the user as "Do you want to replace the existing data?" 2. If user selects as "Yes" - then the data must get replaced. 3. If user selects as "No" - then the data must not get replaced. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
11 | Validate button | To validate the Validate button when the data entered by the user has no errors. |  | Article - 8/5/1 Supplier - Test Validity period - January 2020 Dimension - 10/10/10 | The validation of the data must be successful and the Save button must get enabled. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
12 | Validate button | To validate the Validate button when the data entered by the user has some errors in few rows. |  | Article - 8/ /1 Dimension - 10/10/10 | 1.Appropriate validation messages must be displayed in the same row of the incorrect data. 2.The save button should not get enabled. | Negative | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
13 | Selecting the supplier | To validate the selection of the supplier. |  | Supplier - test | The selected supplier must be displayed in the supplier field. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
14 | Selecting the supplier | To validate the supplier field when no supplier has been selected. |  |  | The supplier must be left blank. | Negative | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
15 | Selecting the Validity period | To validate the selection of the validity period. |  | Validity period - January 2020 | The selected validity period must be displayed in the validity period field. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
16 | Selecting the Validity period | To validate the validity period field when nothing has been selected. |  |  | The validity period field must be blank. | Negative | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
17 | Save the data to Article master - Lieferant | To validate the Save button when the supplier and the Validity period has been selected. |  | Article - 8/5/1 Supplier - Test Validity period - January 2020 Dimension - 10/10/10 | The data must be saved in the article master and the Lieferant form for the selected validity period and the supplier. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
18 | Save the data to Article master - Lieferant | To validate the Save button when the supplier has not been selected. |  | Article - 8/5/1 Validity period - January 2020 Dimension - 10/10/10 | The data must not get saved to the article master. | Negative | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
19 | Save the data to Article master - Lieferant | To validate the Save button when the Validity period has not been selected. |  | Article - 8/5/1 Supplier - Test Dimension - 10/10/10 Default validity period - August 2020 | The data must get saved for the current month by creating the validity period. | Negative | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
20 | Close button | To validate the Close button in the 'Datanorm' main form. |  |  | The 'Datanorm' form must get closed and focus must be returned to the Calc pro ribbon. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
21 | Esc key | To validate the 'Esc' key in the Datanorm main form. |  |  | The 'Datanorm' form must get closed and focus must be returned to the Calcpro ribbon. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020
22 | UI design | To validate the UI design of the Datanorm form. |  |  | All the button, labels texts and all the form design must be correct. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Fail |  |  |  | Waiting for the complete implementation.
23 | Field comparison | To validate all the fields of the Datanorm form. |  |  | All the fields in the OTTO pro tool must be present in the Calc pro Datanorm main form. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
24 | Loading of the form | To validate the loading of the Datanorm form when no projects are loaded |  |  | The 'Datanorm' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
25 | Loading of the form | To validate the loading of the Datanorm form when one project is loaded |  |  | The 'Datanorm' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
26 | Loading of the form | To validate the loading of the Datanorm form when multiple projects are loaded |  |  | The 'Datanorm' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
27 | Loading of the form | To validate loading of the Datanorm form when the focus is on the Dokumente tab of the project. |  |  | The 'Datanorm' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
28 | Dependency | To validate the dependency of the datanorm form in the Article master |  | Article - 8/5/1 Validity period - January 2020 Dimension - 10/10/10 | The validity period, article and its dimensions must be saved in the Article master form. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass
29 | Dependency | To validate the dependency of the datanorm form in the Lieferant form. |  | Supplier - test Article - 8/5/1 | The article - Supplier mapping must be created in the Lieferant form based on the Data and the supplier data in the Datanorm form. | Positive | Preethi | 2020-06-08 | Preethi | 30/07/2020 | Pass

## New user
Module Name: |  | New user
Release Version: |  | 1
Environment tested on(OS/Browser/ExcelVersion/German/English) : |  | German system
Pre-requisites:
Navigation steps:
Module Dependencies: |  | Application- user login
Sno. | Test Scenario | Test Case Description | Test Steps | Test Data | Expected Result | Test Case Type(Positive/Negative) | Test case designed by | Test case design date | Build version 1 | [6 empty] | Build version 2
[9 empty] | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments
1 | Add a new user | To validate adding the new user when all the mandatory fields has been entered. |  | User - test | The new user must get created | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
2 | Add a new user | To validate the adding of the new user when all the mandatory fields are not entered. |  |  | Appropriate warning message must be displayed. | Negative | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
3 | Password reset | To validate the password reset button. |  | For user - test | The password of the selected user must get reset to the Default password. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
4 | Cancel button | To validate the Cancel button in the 'New user' main form. |  |  | The 'New user' form must get closed and focus must be returned to the Calc pro ribbon. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
5 | Close button | To validate the Close button in the 'New user' main form. |  |  | The 'New user' form must get closed and focus must be returned to the Calc pro ribbon. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
6 | Esc key | To validate the 'Esc' key in the New user main form. |  |  | The 'New user' form must get closed and focus must be returned to the Calcpro ribbon. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
7 | UI design | To validate the UI design of the New user form. |  |  | All the button, labels texts and all the form design must be correct. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Fail |  |  |  | Waiting for the new tool.
8 | Field comparison | To validate all the fields of the New user form. |  |  | All the fields in the OTTO pro tool must be present in the Calc pro New user main form. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
9 | Loading of the form | To validate the loading of the New user form when no projects are loaded |  |  | The 'New user' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
10 | Loading of the form | To validate the loading of the New user form when one project is loaded |  |  | The 'New user' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
11 | Loading of the form | To validate the loading of the New user form when multiple projects are loaded |  |  | The 'New user' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
12 | Loading of the form | To validate loading of the New user form when the focus is on the Dokumente tab of the project. |  |  | The 'New user' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
13 | Dependency | To validate the dependency of the new user created in the user login form. |  |  | The created user must be able to login to the application, by using the default password. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass

## Roles
Module Name: |  | Access rights
Release Version: |  | 1
Environment tested on(OS/Browser/ExcelVersion/German/English) : |  | German system
Pre-requisites:
Navigation steps:
Module Dependencies: |  | All the forms based on the roles
Sno. | Test Scenario | Test Case Description | Test Steps | Test Data | Expected Result | Test Case Type(Positive/Negative) | Test case designed by | Test case design date | Build version 1 | [6 empty] | Build version 2
[9 empty] | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments
1 | Changing the access rights | To validate the change of the access rights for one form |  | Role - Administrator | 1.The change to the access rights must be saved. 2. The access rights of the other roles must not be changed. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
2 | Changing the access rights | To validate the change of the access rights of all the forms |  |  | 1.The change to the access rights must be saved. 2. The access rights of the other roles must not be changed. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
3 | Password reset | To validate the password reset button. |  |  | The password of the selected user must get reset to the Default password. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
4 | Close button | To validate the Close button in the 'New user' main form. |  |  | The 'New user' form must get closed and focus must be returned to the Calc pro ribbon. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
5 | Esc key | To validate the 'Esc' key in the Access rights main form. |  |  | The 'Access rights' form must get closed and focus must be returned to the Calcpro ribbon. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
6 | UI design | To validate the UI design of the Access rights form. |  |  | All the button, labels texts and all the form design must be correct. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Fail |  |  |  | Waiting for the new tool.
7 | Field comparison | To validate all the fields of the Access rights form. |  |  | All the fields in the OTTO pro tool must be present in the Calc pro Access rights main form. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
8 | Loading of the form | To validate the loading of the Access rights form when no projects are loaded |  |  | The 'Access rights' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
9 | Loading of the form | To validate the loading of the Access rights form when one project is loaded |  |  | The 'Access rights' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
10 | Loading of the form | To validate the loading of the Access rights form when multiple projects are loaded |  |  | The 'Access rights' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
11 | Loading of the form | To validate loading of the Access rights form when the focus is on the Dokumente tab of the project. |  |  | The 'Access rights' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass
12 | Dependency | To validate the dependency of the Access rights created in the all the forms for the specific role user. |  | Role - Administrator having all the rights for the forms as R/W | The access rights of all the form, must work as specified in the access rights form for the specific role user. | Positive | Preethi | 2020-06-08 | Preethi | 2020-01-08 | Pass

## Project creation form
Module Name: |  | New project creation form
Release Version: |  | 1
Environment tested on(OS/Browser/ExcelVersion/German/English) : |  | German system
Pre-requisites:
Navigation steps:
Module Dependencies: |  | LV details
Sno. | Test Scenario | Test Case Description | Test Steps | Test Data | Expected Result | Test Case Type(Positive/Negative) | Test case designed by | Test case design date | Build version 1 | [6 empty] | Build version 2
[9 empty] | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments
1 | Creating a new project | To validate the creation of the new project by entering all the fields of the form |  |  | The project must get created with all the fields entered. | Positive | Preethi | 2020-07-08 | Preethi |  | Pass
2 | Creating a new project | To validate the creation of the new project by entering the mandatory fields of the form. |  |  | The project must get created with the mandatory fields entered. | Positive | Preethi | 2020-07-08 | Preethi |  | Pass
3 | Creating a new project | To validate the creation of the new project without entering the mandatory fields. |  |  | Appropriate warning symbol must be displayed "Please enter the mandatory fields". | Negative | Preethi | 2020-07-08 | Preethi |  | Pass
4 | Creating a new project | To validate the saving of the project with the project name that already exists. |  |  | Appropriate warning symbol must be displayed "Project name already exists". | Negative
5 | Updating the project | To validate the saving of the project on updating all the fields |  |  | The changes made to the fields must be saved to the project. | Positive | Preethi | 2020-06-08 | Preethi
6 | Updating the project | To validate the updating of one field of the project |  |  | The changes made to the fields must be saved to the project. | Positive | Preethi | 2020-06-08 | Preethi
7 | Updating the project | To validate the saving of the project without making any changes to any fields |  |  | The save must be successful. | Negative | Preethi | 2020-06-08 | Preethi
8 | Schlussparagraph Angebot | To validate the Schlussparagraph Angebot button |  |  | The data entered in the section must get saved for the project. | Positive | Preethi | 2020-06-08 | Preethi
9 | Schlussparagraph Angebot | To validate updating of the data in the Schlussparagraph Angebot button |  |  | The updated data must get saved for the project. | Positive | Preethi | 2020-06-08 | Preethi
10 | Kommentar Kalkulator | To validate the Kommentar Kalkulator button |  |  | The data entered in the section must get saved for the project. | Positive | Preethi | 2020-06-08 | Preethi
11 | Kommentar Kalkulator | To validate updating of the data in the Kommentar Kalkulator button |  |  | The updated data must get saved for the project. | Positive | Preethi | 2020-06-08 | Preethi
12 | Discount position | To validate the Discount position creation |  |  | 1.The discount position must get saved for the project. 2.The discount entry must be displayed in the LV details for the respective title/subtitle added for. | Positive | Preethi | 2020-06-08 | Preethi
13 | Delete - Discount position | To validate the deletion of the discount position |  |  | 1.The discount position must get deleted from the project. 2.The discount position must get deleted from the LV details also. | Positive | Preethi | 2020-06-08 | Preethi
14 | Commission | To validate the changing the project into commission |  |  | 1. The confirmation pop up must be displayed, "Are you sure to change the project to commission". 2. On clicking yes, the project must be saved as commission project. | Positive | Preethi | 2020-06-08 | Preethi
15 | Commission | To validate duplicate name in the Kommission nr field. |  |  | Appropriate message must be displayed, "Commission number already exists". | Negative | Preethi | 2020-06-08 | Preethi
16 | Close button | To validate the close button of the project creation form |  |  | The project creation form must be closed. | Positive | Preethi | 2020-06-08 | Preethi
17 | Loading Multiple projects | To validate saving of the project when multiple projects has been loaded. |  |  | The data entered for one project must not conflict with other projects. | Positive | Preethi | 2020-06-08 | Preethi
18 | Loading Multiple projects | To validate updating of the fields of the project when multiple projects has been loaded. |  |  | The data entered for one project must not conflict with other projects. | Positive | Preethi | 2020-06-08 | Preethi
19 | UI design | To validate the UI design of the Project creation form. |  |  | All the button, labels texts and all the form design must be correct. | Positive | Preethi | 2020-06-08 | Preethi
20 | Field comparison | To validate all the fields of the Project creation form. |  |  | All the fields in the OTTO pro tool must be present in the Calc pro Project creation main form. | Positive | Preethi | 2020-06-08 | Preethi
21 | Loading of the form | To validate the loading of the Project creation form when no projects are loaded |  |  | The 'Project creation' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi
22 | Loading of the form | To validate the loading of the Project creation form when one project is loaded |  |  | The 'Project creation' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi
23 | Loading of the form | To validate the loading of the Project creation form when multiple projects are loaded |  |  | The 'Project creation' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi
24 | Loading of the form | To validate loading of the Project creation form when the focus is on the Dokumente tab of the project. |  |  | The 'Project creation' form should be loaded without any problem. | Positive | Preethi | 2020-06-08 | Preethi
25 | Dependency | To validate the dependency of the Project creation form in the LV details |  |  | The values populated in the LV details must be based on the selection and the entry made in the Project creation form. | Positive | Preethi | 2020-06-08 | Preethi

## LV Details
Module Name: |  | LV details
Release Version: |  | 1
Environment tested on(OS/Browser/ExcelVersion/German/English) : |  | German system
Pre-requisites:
Navigation steps:
Module Dependencies:
Sno. | Test Scenario | Test Case Description | Test Steps | Test Data | Expected Result | Test Case Type(Positive/Negative) | Test case designed by | Test case design date | Build version 1 | [6 empty] | Build version 2
[9 empty] | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments
1 | New button - Create title | To validate the creation of the Title position. |  |  | The title must get created. | Positive | Preethi | 2020-07-08 | Preethi
2 | New button - Create subtitle | To validate the creation of the Subtitle position. |  |  | The subtitle must get created. | Positive | Preethi | 2020-07-08 | Preethi
3 | New button - Create positions | To validate the creation of the Positions |  | N | The Normal position must get created | Positive | Preethi | 2020-07-08 | Preethi
4 | New button - Create positions | To validate the creation of the position |  | P | The Pauschal position must get created. | Positive | Preethi | 2020-07-08 | Preethi
5 | New button - Create positions | To validate the creation of the position |  | E | The Eventual position must get created | Positive | Preethi | 2020-07-08 | Preethi
6 | New button - Create positions | To validate the creation of the position |  | A | The Alternate position must get created. | Positive | Preethi | 2020-07-08 | Preethi
7 | New button - Create positions | To validate the creation of the position |  | M | The M position must get created. | Positive | Preethi | 2020-07-08 | Preethi
8 | New button - Create positions | To validate the creation of the position |  | ZS | The Summe position must get created. | Positive | Preethi | 2020-07-08 | Preethi
9 | New button - Create positions | To validate the creation of the position |  | Z | The Surcharge position must get createed. | Positive | Preethi | 2020-07-08 | Preethi
10 | New button - Create positions | To validate the creation of the position |  | Text position | The text position must get created. | Positive | Preethi | 2020-07-08 | Preethi
11 | New continuous button - Create title | To validate the creation of the title position, using the new continuous button. |  |  | The title must get created | Positive | Preethi | 2020-07-08 | Preethi
12 | New continuous button - Create sub title | To validate the creation of the subtitle position, using the new continuous button. |  |  | The subtitle must get created. | Positive | Preethi | 2020-07-08 | Preethi
13 | New continuous button - Create positions | To validate the creation of the positions using the new continuous button. |  |  | The positions must get created. | Positive | Preethi | 2020-07-08 | Preethi
14 | Create position | To validate the creation of the position without entering the mandatory fields |  |  | Appropriate warning message or the symbol must be displayed. | Negative |  | 2020-07-08 | Preethi
15 | Update position - LV details view | To validate the updating of the position for one field in the LV details view. |  | One field | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-07-08 | Preethi
16 | Update position - LV details view | To validate the updating of the position for all the fields in the LV details view. |  | All the fields | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-07-08 | Preethi
17 | Accessories - LV details | To validate creation of the accessories in the LV details view |  |  | 1.The accessory position must be created. 2.All the details of the base position must be copied to the accessory position. | Positive | Preethi | 2020-07-08 | Preethi
18 | Copy position - LV details view | To validate the copy of the positions in the LV details view |  |  | The copy of the position created must have the values equal to the position from which it has been copied. | Positive | Preethi | 2020-07-08 | Preethi
19 | Delete position - LV details view | To validate the deletion of the position in the LV details view |  |  | 1.The position must be deleted. 2. The value of the deleted position must be reduced from its subtitle and the title position. | Positive | Preethi | 2020-07-08 | Preethi
20 | Update position - Cost details view | To validate the updating of the position for one field in the Cost details view. |  |  | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-07-08 | Preethi
21 | Update position - Cost details view | To validate the updating of the position for all the fields in the Cost details view. |  |  | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-07-08 | Preethi
22 | Accessories - Cost details view | To validate the creation of the accessories in the cost details view. |  |  | 1.The accessory position must be created. 2.All the details of the base position must be copied to the accessory position. | Positive | Preethi | 2020-07-08 | Preethi
23 | Copy position - Cost details view | To validate the copy of the positions in the Cost details view |  |  | The copy of the position created must have the values equal to the position from which it has been copied. | Positive | Preethi | 2020-07-08 | Preethi
24 | Delete position - Cost details view | To validate the deletion of the position in the Cost details view |  |  | 1.The position must be deleted. 2. The value of the deleted position must be reduced from its subtitle and the title position. | Positive | Preethi | 2020-07-08 | Preethi
25 | Update position - Cost details w/o grid view | To validate the updating of the position for one field in the Cost details w/o grid view. |  |  | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-07-08 | Preethi
26 | Update position - Cost details w/o grid view | To validate the updating of the position for all the fields in the Cost details w/o grid view. |  |  | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-07-08 | Preethi
27 | Accessories - Cost details w/o grid view | To validate the creation of the accessories position in the cost details w/o grid view |  |  | 1.The accessory position must be created. 2.All the details of the base position must be copied to the accessory position. | Positive | Preethi | 2020-07-08 | Preethi
28 | Copy position - Cost details w/o grid view | To validate the copy of the positions in the Cost details w/o grid view |  |  | The copy of the position created must have the values equal to the position from which it has been copied. | Positive | Preethi | 2020-07-08 | Preethi
23 | Delete position - Cost details w/o grid view | To validate the deletion of the position in the Cost details w/o grid view |  |  | 1.The position must be deleted. 2. The value of the deleted position must be reduced from its subtitle and the title position. | Positive | Preethi | 2020-07-08 | Preethi
24 | Update position - Tree view | To validate the updating of the position for one field in the Tree view. |  |  | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-07-08 | Preethi
25 | Update position - Tree view | To validate the updating of the position for all the fields in the Tree view. |  |  | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-07-08 | Preethi
26 | Copy position - Treeview | To validate the copy of the positions in the Treeview |  |  | The copy of the position created must have the values equal to the position from which it has been copied. | Positive | Preethi | 2020-07-08 | Preethi
27 | Delete position - Tree view | To validate the deletion of the position in the Tree view |  |  | 1.The position must be deleted. 2. The value of the deleted position must be reduced from its subtitle and the title position. | Positive | Preethi | 2020-07-08 | Preethi
28 | Drag and drop of position - Tree view | To validate the drag and drop of the position within the Subtitle |  |  | The position must be relocated from the original position to the new location within the Subtitle. | Positive | Preethi | 2020-07-08 | Preethi
29 | Drag and drop of position - Tree view | To validate the drag and drop of the position within the Title |  |  | The position must be relocated from the original position to the new location within the Title. | Positive | Preethi | 2020-07-08 | Preethi
30 | Drag and drop of position - Tree view | To validate the drag and drop of the position to different title. |  |  | The position must be relocated from the original position to the new location in a different Title. | Positive | Preethi | 2020-07-08 | Preethi
31 | Detail KZ position - Tree view | To validate the creation of the detail KZ position level 1. |  |  | 1.The detail KZ '1' must be created. 2.The details of the base position must be transferred to the detail KZ position. | Positive | Preethi | 2020-07-08 | Preethi
32 | Detail KZ position - Tree view | To validate the creation of the detail KZ position from the level 1. |  |  | 1.The detail KZ '2' must be created. 2.The detail KZ '2' must be created with blank value but the Pos KZ must be copied from the Detail KZ '1'. | Positive | Preethi | 2020-07-08 | Preethi
33 | Detail KZ position - Tree view | To validate the creation of the detail KZ position from base position already having the Detail KZ position. |  |  | 1. Appropriate message must be displayed, "Detail KZ position already exists". | Negative | Preethi | 2020-08-10 | Preethi
34 | Refresh button | To validate the Refresh button for Surcharge position |  |  | The Surcharge position must be calculated based on the position range. | Positive | Preethi | 2020-08-10 | Preethi
35 | Refresh button | To validate the Refresh button for subtitle. |  |  | The value of the Subtitle must be calculated based on the positions in the Subtitle. | Positive | Preethi | 2020-08-10 | Preethi
36 | Refresh button | To validate the Refresh button for Title. |  |  | The value of the Subtitle must be calculated based on the positions in the Title. | Positive | Preethi | 2020-08-10 | Preethi
37 | Refresh button | To validate the order of the positions after clicking on the Refresh button for the Text positions |  |  | All the positions must be sorted appropriately. | Positive | Preethi | 2020-08-10 | Preethi
38 | Refresh button | To validate the order of the positions after clicking on the Refresh button for the Detail KZ position. |  |  | All the Detail KZ positions must be sorted in the order appropriately. | Positive | Preethi | 2020-08-10 | Preethi
39 | Refresh button | To validate the Refresh button click multiple times without any changes. |  |  | The data must get refreshed without any error. | Negative | Preethi | 2020-08-10 | Preethi
40 | Cancel button | To validate the Cancel button. |  |  | The current action must get Cancelled. | Positive | Preethi | 2020-08-10 | Preethi
After commission
41 | New button - Create title | To validate the creation of the Title position. |  |  | The title must get created. | Positive | Preethi | 2020-08-10 | Preethi
42 | New button - Create subtitle | To validate the creation of the Subtitle position. |  |  | The subtitle must get created. | Positive | Preethi | 2020-08-10 | Preethi
43 | New button - Create positions | To validate the creation of the Positions |  | N | The Normal position must get created | Positive | Preethi | 2020-08-10 | Preethi
44 | New button - Create positions | To validate the creation of the position |  | P | The Pauschal position must get created. | Positive | Preethi | 2020-08-10 | Preethi
45 | New button - Create positions | To validate the creation of the position |  | E | The Eventual position must get created | Positive | Preethi | 2020-08-10 | Preethi
46 | New button - Create positions | To validate the creation of the position |  | A | The Alternate position must get created. | Positive | Preethi | 2020-08-10 | Preethi
47 | New button - Create positions | To validate the creation of the position |  | M | The M position must get created. | Positive | Preethi | 2020-08-10 | Preethi
48 | New button - Create positions | To validate the creation of the position |  | ZS | The Summe position must get created. | Positive | Preethi | 2020-08-10 | Preethi
49 | New button - Create positions | To validate the creation of the position |  | Z | The Surcharge position must get createed. | Positive | Preethi | 2020-08-10 | Preethi
50 | New button - Create positions | To validate the creation of the position |  | Text position | The text position must get created. | Positive | Preethi | 2020-08-10 | Preethi
51 | New continuous button - Create title | To validate the creation of the title position, using the new continuous button. |  |  | The title must get created | Positive | Preethi | 2020-08-10 | Preethi
52 | New continuous button - Create sub title | To validate the creation of the subtitle position, using the new continuous button. |  |  | The subtitle must get created. | Positive | Preethi | 2020-08-10 | Preethi
53 | New continuous button - Create positions | To validate the creation of the positions using the new continuous button. |  |  | The positions must get created. | Positive | Preethi | 2020-08-10 | Preethi
54 | Create position | To validate the creation of the position without entering the mandatory fields |  |  | Appropriate warning message or the symbol must be displayed. | Negative | Preethi | 2020-08-10 | Preethi
55 | Update position - LV details view | To validate the updating of the position for one field in the LV details view. |  | One field | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-08-10 | Preethi
56 | Update position - LV details view | To validate the updating of the position for all the fields in the LV details view. |  | All the fields | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-08-10 | Preethi
57 | Accessories - LV details | To validate creation of the accessories in the LV details view |  |  | 1.The accessory position must be created. 2.All the details of the base position must be copied to the accessory position. | Positive | Preethi | 2020-08-10 | Preethi
58 | Copy position - LV details view | To validate the copy of the positions in the LV details view |  |  | The copy of the position created must have the values equal to the position from which it has been copied. | Positive | Preethi | 2020-08-10 | Preethi
59 | Delete position - LV details view | To validate the deletion of the position in the LV details view |  |  | 1.The position must be deleted. 2. The value of the deleted position must be reduced from its subtitle and the title position. | Positive | Preethi | 2020-08-10 | Preethi
60 | Update position - Cost details view | To validate the updating of the position for one field in the Cost details view. |  |  | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-08-10 | Preethi
61 | Update position - Cost details view | To validate the updating of the position for all the fields in the Cost details view. |  |  | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-08-10 | Preethi
62 | Accessories - Cost details view | To validate the creation of the accessories in the cost details view. |  |  | 1.The accessory position must be created. 2.All the details of the base position must be copied to the accessory position. | Positive | Preethi | 2020-08-10 | Preethi
63 | Copy position - Cost details view | To validate the copy of the positions in the Cost details view |  |  | The copy of the position created must have the values equal to the position from which it has been copied. | Positive | Preethi | 2020-08-10 | Preethi
64 | Delete position - Cost details view | To validate the deletion of the position in the Cost details view |  |  | 1.The position must be deleted. 2. The value of the deleted position must be reduced from its subtitle and the title position. | Positive | Preethi | 2020-08-10 | Preethi
65 | Update position - Cost details w/o grid view | To validate the updating of the position for one field in the Cost details w/o grid view. |  |  | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-08-10 | Preethi
66 | Update position - Cost details w/o grid view | To validate the updating of the position for all the fields in the Cost details w/o grid view. |  |  | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-08-10 | Preethi
67 | Accessories - Cost details w/o grid view | To validate the creation of the accessories position in the cost details w/o grid view |  |  | 1.The accessory position must be created. 2.All the details of the base position must be copied to the accessory position. | Positive | Preethi | 2020-08-10 | Preethi
68 | Copy position - Cost details w/o grid view | To validate the copy of the positions in the Cost details w/o grid view |  |  | The copy of the position created must have the values equal to the position from which it has been copied. | Positive | Preethi | 2020-08-10 | Preethi
69 | Delete position - Cost details w/o grid view | To validate the deletion of the position in the Cost details w/o grid view |  |  | 1.The position must be deleted. 2. The value of the deleted position must be reduced from its subtitle and the title position. | Positive | Preethi | 2020-08-10 | Preethi
70 | Update position - Tree view | To validate the updating of the position for one field in the Tree view. |  |  | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-08-10 | Preethi
71 | Update position - Tree view | To validate the updating of the position for all the fields in the Tree view. |  |  | 1.The changes made to the positions must be saved. 2. The changes must reflect when the position is loaded again. | Positive | Preethi | 2020-08-10 | Preethi
72 | Copy position - Treeview | To validate the copy of the positions in the Treeview |  |  | The copy of the position created must have the values equal to the position from which it has been copied. | Positive | Preethi | 2020-08-10 | Preethi
73 | Delete position - Tree view | To validate the deletion of the position in the Tree view |  |  | 1.The position must be deleted. 2. The value of the deleted position must be reduced from its subtitle and the title position. | Positive | Preethi | 2020-08-10 | Preethi
74 | Drag and drop of position - Tree view | To validate the drag and drop of the position within the Subtitle |  |  | The position must be relocated from the original position to the new location within the Subtitle. | Positive | Preethi | 2020-08-10 | Preethi
75 | Drag and drop of position - Tree view | To validate the drag and drop of the position within the Title |  |  | The position must be relocated from the original position to the new location within the Title. | Positive | Preethi | 2020-08-10 | Preethi
76 | Drag and drop of position - Tree view | To validate the drag and drop of the position to different title. |  |  | The position must be relocated from the original position to the new location in a different Title. | Positive | Preethi | 2020-08-10 | Preethi
77 | Detail KZ position - Tree view | To validate the creation of the detail KZ position level 1. |  |  | 1.The detail KZ '1' must be created. 2.The details of the base position must be transferred to the detail KZ position. | Positive | Preethi | 2020-08-10 | Preethi
78 | Detail KZ position - Tree view | To validate the creation of the detail KZ position from the level 1. |  |  | 1.The detail KZ '2' must be created. 2.The detail KZ '2' must be created with blank value but the Pos KZ must be copied from the Detail KZ '1'. | Positive | Preethi | 2020-08-10 | Preethi
79 | Detail KZ position - Tree view | To validate the creation of the detail KZ position from base position already having the Detail KZ position. |  |  | 1. Appropriate message must be displayed, "Detail KZ position already exists". | Negative | Preethi | 2020-08-10 | Preethi
80 | Refresh button | To validate the Refresh button for Surcharge position |  |  | The Surcharge position must be calculated based on the position range. | Positive | Preethi | 2020-08-10 | Preethi
81 | Refresh button | To validate the Refresh button for subtitle. |  |  | The value of the Subtitle must be calculated based on the positions in the Subtitle. | Positive | Preethi | 2020-08-10 | Preethi
82 | Refresh button | To validate the Refresh button for Title. |  |  | The value of the Subtitle must be calculated based on the positions in the Title. | Positive | Preethi | 2020-08-10 | Preethi
83 | Refresh button | To validate the order of the positions after clicking on the Refresh button for the Text positions |  |  | All the positions must be sorted appropriately. | Positive | Preethi | 2020-08-10 | Preethi
84 | Refresh button | To validate the order of the positions after clicking on the Refresh button for the Detail KZ position. |  |  | All the Detail KZ positions must be sorted in the order appropriately. | Positive | Preethi | 2020-08-10 | Preethi
85 | Refresh button | To validate the Refresh button click multiple times without any changes. |  |  | The data must get refreshed without any error. | Negative | Preethi | 2020-08-10 | Preethi
86 | Cancel button | To validate the Cancel button. |  |  | The current action must get Cancelled. | Positive | Preethi | 2020-08-10 | Preethi
87 | UI design | To validate the UI design of the LV details form. |  |  | All the button, labels texts and all the form design must be correct. | Positive | Preethi | 2020-08-10 | Preethi
88 | Field comparison | To validate all the fields of the LV details form. |  |  | All the fields in the OTTO pro tool must be present in the Calc pro LV details main form. | Positive | Preethi | 2020-08-10 | Preethi
89 | Loading of the form | To validate the loading of the LV details form when no projects are loaded |  |  | The 'LV details' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi
90 | Loading of the form | To validate the loading of the LV details form when one project is loaded |  |  | The 'LV details' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi
91 | Loading of the form | To validate the loading of the LV details form when multiple projects are loaded |  |  | The 'LV details' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi
92 | Loading of the form | To validate loading of the LV details form when the focus is on the Dokumente tab of the project. |  |  | The 'LV details' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi

## Bulk operation
Module Name: |  | Bulk operation
Release Version: |  | 1
Environment tested on(OS/Browser/ExcelVersion/German/English) : |  | German system
Pre-requisites:
Navigation steps:
Module Dependencies: |  | LV details
Sno. | Test Scenario | Test Case Description | Test Steps | Test Data | Expected Result | Test Case Type(Positive/Negative) | Test case designed by | Test case design date | Build version 1 | [6 empty] | Build version 2
[9 empty] | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments
1 | Filtering | To validate the filter by using the 'Title/Subtitle' option. |  |  | The positions must be filtered based on title or the subtitle entered | Positive | Preethi | 2020-08-10 | Preethi
2 | Filtering | To validate the filter by using the 'Position' option. |  |  | The positions must be filtered based on Positions entered | Positive | Preethi | 2020-08-10 | Preethi
3 | Filtering | To validate the filter by using the WG/WA option. |  |  | The positions must be filtered based on WG-WA entered | Positive | Preethi | 2020-08-10 | Preethi
4 | Filtering | To validate the apply filter button, when no filter criteria is entered. |  |  | Appropriate validation message or the symbol must be displayed. | Negative | Preethi | 2020-08-10 | Preethi
5 | Action A | To validate the applying of the value in Action A section |  |  | The value entered for the field must get saved to all the positions under the filtered criteria. | Positive | Preethi | 2020-08-10 | Preethi
6 | Action A | To validate applying of all the the values in the Action A section |  |  | The values entered for all the fields must get saved to all the positions under the filtered criteria. | Positive | Preethi | 2020-08-10 | Preethi
7 | Action A | To validate the removal of the values in the Action A |  |  | The value must set to the Default value for the field selected for all the positions in the filtered criteria. | Positive | Preethi | 2020-08-10 | Preethi
8 | Action A | To validate the removal of the all the values in Action A |  |  | The value must set to the Default value for all the fields selected for all the positions in the filtered criteria. | Positive | Preethi | 2020-08-10 | Preethi
9 | Action A | To validate the Save button when no data has been entered. |  |  | Appropriate validation message or the symbol must be displayed. | Negative | Preethi | 2020-08-10 | Preethi
10 | Action B | To validate the applying of the value in Action B section |  |  | The value entered for the field must get saved to all the positions under the filtered criteria. | Positive | Preethi | 2020-08-10 | Preethi
11 | Action B | To validate applying of all the the values in the Action B section |  |  | The values entered for all the fields must get saved to all the positions under the filtered criteria. | Positive | Preethi | 2020-08-10 | Preethi
12 | Action B | To validate the removal of the values in the Action B |  |  | The value must set to the Default value for the field selected for all the positions in the filtered criteria. | Positive | Preethi | 2020-08-10 | Preethi
13 | Action B | To validate the removal of the all the values in Action B |  |  | The value must set to the Default value for all the fields selected for all the positions in the filtered criteria. | Positive | Preethi | 2020-08-10 | Preethi
14 | Action B | To validate the Save button when no data has been entered. |  |  | Appropriate validation message or the symbol must be displayed. | Negative | Preethi | 2020-08-10 | Preethi
15 | UI design | To validate the UI design of the Bulk operation form. |  |  | All the button, labels texts and all the form design must be correct. | Positive | Preethi | 2020-08-10 | Preethi
16 | Field comparison | To validate all the fields of the Bulk operation form. |  |  | All the fields in the OTTO pro tool must be present in the Calc pro Bulk operation main form. | Positive | Preethi | 2020-08-10 | Preethi
17 | Loading of the form | To validate the loading of the Bulk operation form when no projects are loaded |  |  | The 'Bulk operation' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi
18 | Loading of the form | To validate the loading of the Bulk operation form when one project is loaded |  |  | The 'Bulk operation' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi
19 | Loading of the form | To validate the loading of the Bulk operation form when multiple projects are loaded |  |  | The 'Bulk operation' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi
20 | Loading of the form | To validate loading of the Bulk operation form when the focus is on the Dokumente tab of the project. |  |  | The 'Bulk operation' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi
21 | Dependency | To validate the saving or removing of the values to the positions in LV details from the Bulk operation. |  |  | The values saved or removed for the fields, from Bulk operation form must be reflected in LV details position. | Positive | Preethi | 2020-08-10 | Preethi

## Selbstkosten
Module Name: |  | Selbstkosten
Release Version: |  | 1
Environment tested on(OS/Browser/ExcelVersion/German/English) : |  | German system
Pre-requisites:
Navigation steps:
Module Dependencies: |  | LV details
Sno. | Test Scenario | Test Case Description | Test Steps | Test Data | Expected Result | Test Case Type(Positive/Negative) | Test case designed by | Test case design date | Build version 1 | [6 empty] | Build version 2
[9 empty] | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments
1 | Section 1 | To validate all the articles displayed in the Selbstkosten form. |  |  | 1.All the distinct article present in the LV details must be displayed in the selbstkosten form. 2.Positions for which the multi 5 cells are locked, respective article must not be displayed in the Selbstkosten form. | Positive | Preethi | 2020-08-10 | Preethi
2 | Section 1 | To validate the saving of the value to the Material multi 5 field for article having Material 'X'. |  |  | The value entered must get saved for the respective article. | Positive | Preethi | 2020-08-10 | Preethi
3 | Section 1 | To validate the saving of the value to the Material multi 5 field for article having Material 'S'. |  |  | The value entered must get saved for the respective article. | Positive | Preethi | 2020-08-10 | Preethi
4 | Section 1 | To validate the Saving of the incorrect factor value |  |  | Appropriate error message must be displayed. | Negative | Preethi | 2020-08-10 | Preethi
5 | Section 1 | To validate the values displayed in the 'X' and 'S' fields from positions in the LV details. |  |  | 1.The value must be equal to the sum of the value of all the positions of the article before the multi 5 value is applied. 2. The value must not include the value on position which the multi 5 cells are locked. | Positive | Preethi | 2020-08-10 | Preethi
6 | Section 1 | To validate the values displayed in the 'X' and 'S' factor fields from positions in the LV details. |  |  | The value must be equal to the multi 5 value present for all the position of the article. | Positive | Preethi | 2020-08-10 | Preethi
7 | Section 1 | To validate the Data loaded for the different LV sections selected. |  |  | The data loaded must be based on the positions with multi 5 cells not locked in the LV details and the LV sections. | Positive | Preethi | 2020-08-10 | Preethi
8 | Section 2 | To validate the Data loaded for the different LV sections selected. |  |  | The data displayed must be the data that is last saved from the 'Selbstkosten' form for that particular LV section. | Positive | Preethi | 2020-08-10 | Preethi
9 | Section 2 | To validate the view of the data for thea article having the multi 5 cells locked for the positions in the LV details. |  |  | The data displayed must be the data that is last saved from the 'Selbstkosten' form for that particular LV section irrespective of the locked or unlocked cells. | Positive | Preethi | 2020-08-10 | Preethi
10 | UI design | To validate the UI design of the Selbstkosten form. |  |  | All the button, labels texts and all the form design must be correct. | Positive | Preethi | 2020-08-10 | Preethi
11 | Field comparison | To validate all the fields of the Selbstkosten form. |  |  | All the fields in the OTTO pro tool must be present in the Calc pro Selbstkosten main form. | Positive | Preethi | 2020-08-10 | Preethi
12 | Loading of the form | To validate the loading of the Selbstkosten form when no projects are loaded |  |  | The 'Selbstkosten' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi
13 | Loading of the form | To validate the loading of the Selbstkosten form when one project is loaded |  |  | The 'Selbstkosten' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi
14 | Loading of the form | To validate the loading of the Selbstkosten form when multiple projects are loaded |  |  | The 'Selbstkosten' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi
15 | Loading of the form | To validate loading of the Selbstkosten form when the focus is on the Dokumente tab of the project. |  |  | The 'Selbstkosten' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi
16 | Dependency | To validate the factor value that is saved from the 'Selbstkosten' form to the positions in the LV details. |  |  | The factor values that is saved from the Selbstkosten form must be reflected in the multi 5 field of the positions in the LV details form. | Positive | Preethi | 2020-08-10 | Preethi

## Verkaufskosten
Module Name: |  | Verkaufskosten
Release Version: |  | 1
Environment tested on(OS/Browser/ExcelVersion/German/English) : |  | German system
Pre-requisites:
Navigation steps:
Module Dependencies: |  | LV details
Sno. | Test Scenario | Test Case Description | Test Steps | Test Data | Expected Result | Test Case Type(Positive/Negative) | Test case designed by | Test case design date | Build version 1 | [6 empty] | Build version 2
[9 empty] | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments | Test case executed by | Execution date | Test case Status | Bugzilla Bug ID | Issue type | Issue Status | Comments
1 | Section 1 | To validate all the articles displayed in the Verkaufskosten form. |  |  | 1.All the distinct article present in the LV details must be displayed in the Verkaufskosten form. 2.Positions for which the multi 6 cells are locked, respective article must not be displayed in the Verkaufskosten form. | Positive | Preethi | 2020-08-10 | Preethi
2 | Section 1 | To validate the saving of the value to the Material multi 6 field for article having Material 'X'. |  |  | The value entered must get saved for the respective article. | Positive | Preethi | 2020-08-10 | Preethi
3 | Section 1 | To validate the saving of the value to the Material multi 6 field for article having Material 'S'. |  |  | The value entered must get saved for the respective article. | Positive | Preethi | 2020-08-10 | Preethi
4 | Section 1 | To validate the Saving of the incorrect factor value |  |  | Appropriate error message must be displayed. | Negative | Preethi | 2020-08-10 | Preethi
5 | Section 1 | To validate the values displayed in the 'X' and 'S' fields from positions in the LV details. |  |  | 1.The value must be equal to the sum of the value of all the positions of the article before the multi 6 value is applied. 2. The value must not include the value on position which the multi 6 cells are locked. | Positive | Preethi | 2020-08-10 | Preethi
6 | Section 1 | To validate the values displayed in the 'X' and 'S' factor fields from positions in the LV details. |  |  | The value must be equal to the multi 6 value present for all the position of the article. | Positive | Preethi | 2020-08-10 | Preethi
7 | Section 1 | To validate the Data loaded for the different LV sections selected. |  |  | The data loaded must be based on the positions with multi 6 cells not locked in the LV details and the LV sections. | Positive | Preethi | 2020-08-10 | Preethi
8 | Section 2 | To validate the Data loaded for the different LV sections selected. |  |  | The data displayed must be the data that is last saved from the 'Verkaufskosten' form for that particular LV section. | Positive | Preethi | 2020-08-10 | Preethi
9 | Section 2 | To validate the view of the data for thea article having the multi 6 cells locked for the positions in the LV details. |  |  | The data displayed must be the data that is last saved from the 'Verkaufskosten' form for that particular LV section irrespective of the locked or unlocked cells. | Positive | Preethi | 2020-08-10 | Preethi
10 | UI design | To validate the UI design of the Verkaufskosten form. |  |  | All the button, labels texts and all the form design must be correct. | Positive | Preethi | 2020-08-10 | Preethi
11 | Field comparison | To validate all the fields of the Verkaufskosten form. |  |  | All the fields in the OTTO pro tool must be present in the Calc pro Verkaufskosten main form. | Positive | Preethi | 2020-08-10 | Preethi
12 | Loading of the form | To validate the loading of the Verkaufskosten form when no projects are loaded |  |  | The 'Verkaufskosten' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi
13 | Loading of the form | To validate the loading of the Verkaufskosten form when one project is loaded |  |  | The 'Verkaufskosten' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi
14 | Loading of the form | To validate the loading of the Verkaufskosten form when multiple projects are loaded |  |  | The 'Verkaufskosten' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi
15 | Loading of the form | To validate loading of the Verkaufskosten form when the focus is on the Dokumente tab of the project. |  |  | The 'Verkaufskosten' form should be loaded without any problem. | Positive | Preethi | 2020-08-10 | Preethi
16 | Dependency | To validate the factor value that is saved from the 'Verkaufskosten' form to the positions in the LV details. |  |  | The factor values that is saved from the 'Verkaufskosten' form must be reflected in the multi 6 field of the positions in the LV details form. | Positive | Preethi | 2020-08-10 | Preethi

## Admin (hidden)
Test case Status | Test case Type | Issue Type | Issue Type description | Issue Status | Issue Status description
Pass | Positive | Functional issue | Based on the requirements if it is not working then it is a functional issue. | Open | When issue has been raised by the tester
Fail | Negative | UI issue | Spelling mistakes, incorrect pop ups/tool tips/button name/navigation buttons, Alignments and placing of the fields and buttons. | Fixed | Issue has been worked by developer
Duplicate |  | Unhandled issue | If there are any unhandled exceptions displayed in the tool. | Closed | Issue fix is working fine and closed by the tester
Invalid |  | Enhancement/Suggestions | Any kind of suggestions from the tester.
Not In Scope